## Taul1
Total hours: | 43
Date | Hours | Work Description
17.01.2019 | 6 | Started project.
20/21.01.2019 | 8 | Very very simple enemy ai, throwable daggers, quick mobile build.
21.01.2019 | 4 | Improved enemy AI.
23.01.2019 | 4 | Started project from scratch, implemented systems for weapons and animations, rewrote input manager and player movement.
26.01.2019 | 6 | Enemy pathfinding with A* algorithm using a grid as nodes.
27.01.2019 | 5 | Started enemy AI.
28.01.2019 | 1 | Enemy AI improvements.
28.01.2019 | 5 | Enemy fights back now yay. It's almost a game.
29.01.2019 | 2 | Gameplay improvements
30.01.2019 | 2 | More gameplay improvements